## Meeting Agenda
Meeting Ethic:
Respect: Treat all team members with respect and value their contributions and ideas.
Active Listening: Listen attentively to each team member during discussions and avoid interrupting.
Collaboration: Encourage open communication and collaboration among team members.
Time Management: Adhere to the meeting agenda and ensure that discussions stay focused and on track.
Accountability: Take ownership of assigned tasks and update the team on progress and challenges.
Constructive Feedback: Provide feedback in a constructive and supportive manner to help improve team performance.
Confidentiality: Maintain the confidentiality of sensitive project information and user data discussed during the meeting.
Professionalism: Maintain a professional and positive attitude throughout the meeting.
Equality: Ensure that all team members have equal opportunity to share their thoughts and opinions.
Problem Solving: Work together to identify and address challenges and find effective solutions.
Agenda:
1. Sprint Review | 2. Sprint Planning
Recap the progress and achievements of the previous sprint. | Review the user stories and tasks for the current sprint.
Discuss any completed user stories or tasks from the previous sprint. | Clarify any doubts or questions regarding the requirements or tasks.
Address any challenges or issues encountered during the previous sprint. | Assign tasks to team members based on their skills and availability.
Estimate the effort required for each task and determine the sprint goal.
3. Daily Stand-up | 4. Sprint Progress
Each team member answers the following three questions: | Track the progress of each user story and task within the current sprint.
What tasks did you complete yesterday? | Update the task board or project management tool with the status of each task.
What tasks will you work on today? | Discuss any issues or delays that may affect the sprint timeline.
Are there any challenges or blockers impeding your progress? | Adjust task priorities or reallocate resources if necessary.
Discuss any dependencies or coordination required between team members.
Encourage collaboration and offer assistance if any team member is facing difficulties.
5. Sprint Retrospective | 6. Sprint Goals and Next Steps
Reflect on the overall sprint performance and team dynamics. | Recap the sprint goals and reiterate the importance of meeting them.
Identify what went well and should be continued in future sprints. | Define specific tasks and targets for the upcoming days.
Discuss any areas for improvement or challenges faced during the sprint. | Confirm any additional requirements, changes, or adjustments to the project plan.
Brainstorm and propose solutions or strategies to address the identified issues. | Communicate any important announcements or updates related to the project.
7. Closing Remarks
Summarize the key points discussed during the meeting.
Emphasize the importance of collaboration, communication, and teamwork.
Confirm the date, time, and agenda for the next scrum meeting.
Encourage team members to reach out for any further clarification or support.
Note: It is essential to adhere to the ethical guidelines and maintain a positive and inclusive environment throughout the scrum meeting. Respectful communication, active participation, and adherence to the agenda will contribute to the successful completion of the online banking system project.

## Sprint Call Sheet
WellsFargo Java Training Sprint Template
PROJECT NAME: ONLINE BANKING SYSTEM - JAVA WITH REACT CASE STUDY |  |  |  | Trainer |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Batch #: |  |  | Group #: |  |  |  | 2023-08-08 | 2023-08-08 | 0% | SCOPE STATEMENT
At Risk? | SPRINT # | USER STORY | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Yes | SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App |  | User 1 |  | 2023-08-08 | 2023-08-08 | 1 | Not Started | High
No |  |  | 2. Install and configure React Router for handling routing in the application |  | User 2 |  | 2023-08-08 | 2023-08-08 |  | Not Started | Medium
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3 |  | 2023-08-08 | 2023-08-08 |  | Not Started | Low
|  | US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the online banking system |  | User 1 |  | 2023-08-09 | 2023-08-09 | 1 | Not Started
|  |  | 2. Create the table for registered users |  | User 2 |  | 2023-08-09 | 2023-08-09 |  | Not Started
|  |  | 3. Create the table for the account |  | User 3 |  | 2023-08-09 | 2023-08-09 |  | Not Started
|  |  | 4. Create the table for Transactions |  | User 4 |  | 2023-08-09 | 2023-08-09 |  | Not Started
|  |  | 5. Populate all the above tables with sample data space |  | User 5 |  | 2023-08-09 | 2023-08-09 |  | Not Started
|  | US_03 - As a frontend developer, create a user registration form that allows end user to fill out details and register as a new user, and have that information securely processed by the backend system. | 1. Create a react page to read user details and provide proper validations at backend |  | User 1 |  | 2023-08-10 | 2023-08-10 | 1 | Not Started
|  |  | 2. Write a proper api end point in springboot to read data from frontend and insert into database |  | User 2 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 3. Perform all sorts of validations using springboot's validators |  | User 3 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  | US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. create a react login page to read username and password |  | User 1 |  | 2023-08-11 | 2023-08-11 | 1 | Not Started
|  |  | 2. Include the Authentication and Authorization techniques |  | User 2 |  | 2023-08-11 | 2023-08-11 |  | Not Started
|  |  | 3.Write a proper api's to read data from front end and implement authentication and authorization using spring security |  | User 3 |  | 2023-08-11 | 2023-08-11 |  | Not Started
|  |  | 4. Implement authentication using JWT |  | User 4 |  | 2023-08-11 | 2023-08-11 |  | Not Started
|  |  | 5. Perform the session management |  | User 5 |  | 2023-08-11 | 2023-08-11 |  | Not Started
|  | US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered users |  | User 1 |  | 2028-08-14 | 2028-08-14 | 1 | Not Started
|  |  | 2. upon successful adding the data, it should generate a unique id, which should also sent along with other details for backend processing. |  | User 2 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 3. Write the backend springboot api's to read account details and add it to database |  | User 3 |  | 2028-08-14 | 2028-08-14 |  | Not Started
Yes | SPRINT - 02 Account Management & User Dashboard | US_06 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components |  | User 1 |  | 2028-08-16 | 2028-08-16 | 1 | Not Started | High
No |  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 2 |  | 2028-08-16 | 2028-08-16 |  | Not Started | Medium
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3 |  | 2028-08-16 | 2028-08-16 |  | Not Started | Low
|  | US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Create form to see customers their balance |  | User 1 |  | 2028-08-17 | 2028-08-17 | 1 | Not Started
|  |  | 2. create form to implement balance check |  | User 2 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  |  | 3. create a form to view transaction history |  | User 3 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  |  | 4. create a form to implement withdrawal functionality |  | User 4 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  | US_08 - As a developer, create the backend to be equipped with the necessary functionality to support and handle all the APIs related to US_7. This will ensure that an end user can seamlessly interact with the application and access the specific features and data associated with US_7. | 1. write the springboot implementation to fetch balance from table and send to UI |  | User 1 |  | 2028-08-18 | 2028-08-18 | 1 | Not Started
|  |  | 2. write the springboot implementation to fetch all transactions for respective user and send to UI |  | User 2 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 3. write the springboot implementation to update the balance after withdrawl of given amount |  | User 3 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  | US_09 - As a developer, create a front end page to perform funds transfer facility and show the transactoin history. | 1. Create a react page to enable funds transfer to self and registered users |  | User 1 |  | 2028-08-21 | 2028-08-21 | 1 | Not Started
|  |  | 2. Perform necessary validations to implement funds transfer facility |  | User 2 |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 3. Create a backend springboot processing to perform the backend operations for funds transfer |  | User 3 |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 4. Create a springboot page to view the transactions history |  | User 4 |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 5. write the backend processing to read the data from database and send it to frontend |  | User 5 |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  | US_10 - As a developer, create a dashboard for admin to have a comprehensive dashboard where admin can perform a variety of activities and manage the system effectively. | 1. Create an UI for admin to display his various operations like, account creation, disabling user, enabling user etc., |  | User 1 |  | 2028-08-22 | 2028-08-22 | 1 | Not Started
|  |  | 2. Create a form to perform user search operation |  | User 2 |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 3. Create form to view all transactions of user |  | User 3 |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 4. Write a backend processing logic to search user details from database and send to frontend UI |  | User 4 |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 5. Write a backend processing logic to retreive transactions of the user from database and send it to frontend UI |  | User 5 |  | 2028-08-22 | 2028-08-22 |  | Not Started
Yes | SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc., |  | User 1 |  | 2028-08-23 | 2028-08-23 | 1 | Not Started | High
No |  |  | Implement the custom exception logic at UI level |  | User 2 |  | 2028-08-23 | 2028-08-23 |  | Not Started | Medium
|  |  | 2. All input validations logic must be performed at UI level |  | User 3 |  | 2028-08-23 | 2028-08-23 |  | Not Started | Low
|  |  | 3. All data validations must be performed at backend |  | User 1 |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  | US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components |  | User 2 |  | 2028-08-24 | 2028-08-24 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 3 |  | 2028-08-24 | 2028-08-24 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 4 |  | 2028-08-25 | 2028-08-25 | 1 | Not Started
|  | US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page |  | User 1 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  |  | 2. Improve the user interface by adding responsive design, styling, and enhancing the user experience |  | User 2 |  | 2028-08-28 | 2028-08-28 | 1 | Not Started
|  |  | 3. Ensure accessibility and compatibility across different browsers |  | User 3 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  | Final Project Presentation |  |  |  |  | 2028-08-29 | 2028-08-29 | 1 | Not Started

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold