## Sheet1
SPRINT # | USER STORY | TASK NAME | FEATURE TYPE | RESPONSIBLE
SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App |  | Isha
|  | 2. Install and configure React Router for handling routing in the application |  | Sankita
|  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | Manan
| US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the online banking system |  | Sankita, manan
|  | 2. Create the table for registered users |  | Sankita, manan
|  | 3. Create the table for the account |  | Sankita
|  | 4. Create the table for Transactions |  | Manan
|  | 5. Populate all the above tables with sample data space |  | Manan
| US_03 - As a frontend developer, create a user registration form that allows end user to fill out details and register as a new user, and have that information securely processed by the backend system. | 1. Create a react page to read user details and provide proper validations at backend |  | Isha
|  | 2. Write a proper api end point in springboot to read data from frontend and insert into database |  | Manan
|  | 3. Perform all sorts of validations using springboot's validators |  | User 3
| US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. create a react login page to read username and password |  | User 1
|  | 2. Include the Authentication and Authorization techniques |  | User 2
|  | 3.Write a proper api's to read data from front end and implement authentication and authorization using spring security |  | User 3
|  | 4. Implement authentication using JWT |  | User 4
|  | 5. Perform the session management |  | User 5
| US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered users |  | User 1
|  | 2. upon successful adding the data, it should generate a unique id, which should also sent along with other details for backend processing. |  | User 2
|  | 3. Write the backend springboot api's to read account details and add it to database |  | User 3
SPRINT - 02 Account Management & User Dashboard | US_06 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components |  | User 1
|  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 2
|  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3
| US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Create form to see customers their balance |  | User 1
|  | 2. create form to implement balance check |  | User 2
|  | 3. create a form to view transaction history |  | User 3
|  | 4. create a form to implement withdrawal functionality |  | User 4
| US_08 - As a developer, create the backend to be equipped with the necessary functionality to support and handle all the APIs related to US_7. This will ensure that an end user can seamlessly interact with the application and access the specific features and data associated with US_7. | 1. write the springboot implementation to fetch balance from table and send to UI |  | User 1
|  | 2. write the springboot implementation to fetch all transactions for respective user and send to UI |  | User 2
|  | 3. write the springboot implementation to update the balance after withdrawl of given amount |  | User 3
| US_09 - As a developer, create a front end page to perform funds transfer facility and show the transactoin history. | 1. Create a react page to enable funds transfer to self and registered users |  | User 1
|  | 2. Perform necessary validations to implement funds transfer facility |  | User 2
|  | 3. Create a backend springboot processing to perform the backend operations for funds transfer |  | User 3
|  | 4. Create a springboot page to view the transactions history |  | User 4
|  | 5. write the backend processing to read the data from database and send it to frontend |  | User 5
| US_10 - As a developer, create a dashboard for admin to have a comprehensive dashboard where admin can perform a variety of activities and manage the system effectively. | 1. Create an UI for admin to display his various operations like, account creation, disabling user, enabling user etc., |  | User 1
|  | 2. Create a form to perform user search operation |  | User 2
|  | 3. Create form to view all transactions of user |  | User 3
|  | 4. Write a backend processing logic to search user details from database and send to frontend UI |  | User 4
|  | 5. Write a backend processing logic to retreive transactions of the user from database and send it to frontend UI |  | User 5
SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc., |  | User 1
|  | Implement the custom exception logic at UI level |  | User 2
|  | 2. All input validations logic must be performed at UI level |  | User 3
|  | 3. All data validations must be performed at backend |  | User 1
| US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components |  | User 2
|  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 3
|  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 4
| US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page |  | User 1
|  | 2. Improve the user interface by adding responsive design, styling, and enhancing the user experience |  | User 2
|  | 3. Ensure accessibility and compatibility across different browsers |  | User 3
Final Project Presentation